## Outputs
|  | Country | Source- Please fill in if new | Description | Is it completed? (even if in modified form) | If complete, provide a short narrative on level of completion and significance of the activity for your programme | Main level where activity takes place-district, national, regional, global. | Primary WASH sub-sector | Is it mostly relevant for rural, Urban, mixed/both ? | Which intermediate outcome does this best correspond to? | Which building block? | Link
# | Type | Country | Source | Description of Activity from Annual Plan | Completion | Narrative | Level | WASH Sub-Sector | Rural,Uban, mixed | Outcome | Building Block | Link
1 | Output | Burkina Faso | Plan | Providing technical assistance and capacity building to the new district authorities in Banfora and Tenkodogo | Yes | Banfora and Tenkodogo masterplans are currently being implemented, even though IRC's financing for Banfora with Hilton has ended in 2023. 5 new district masterplans and 3 regional masterplans were drawn up in 2022 with funding from the European Union. |  | WASH | Mixed | Strong Systems | Institutions
2 | Output | Burkina Faso | Plan | Providing technical assistance to the national authorities for operationalizing the nexus humanitarian, development and peace in the planning and monitoring of the WASH sector | Yes |  |  | WASH | Mixed | Strong Systems | National
3 | Output | Ethiopia | Plan | National guidelines on District-wide approaches and its rolling out with partners, national WASH financing strategy and the subsequent implementation with partners as well as learning paper on area-wide approaches.
4 | Output | Ethiopia | Plan | Tracking district master plan implementations in six districts (North Mecha, Farta, Dera, Negelle Arsi, Shashamane and South Ari) through annual budget and expenditure tracking
5 | Output | Ethiopia | Plan | Support on piloting water safety planning as entry to raise communities’ awareness for demand for improved WASH services in South Ari as well as on strengthening government-led monitoring in Amhara region and South Omo zone as part of scaling up.
6 | Output | Ethiopia | Plan | Support to partner districts on resource mobilization for master plan implementation, and action research on market-based sanitation and deliver budget and expenditure tracking, research and monitoring reports.
7 | Output | Ethiopia | Plan | Supporting country engagement in key global sector events including All systems connect planned for May 2023, and UN 2023 Water conference planned for March 2023.
8 | Output | Ghana | Plan | Training event for at least 30 persons using the WASH Systems Academy (LGSS, NDPC, RCCs etc) - District planning for sustainable WASH services | Yes | IRC, in collaboration with the National Development Planning Commission (NDPC), held a District Panning for Sustainable WASH Services training workshop in Ghana at the City Escape Hotel Prampram, Ghana. The participants were from the 16 Regional Coordination Councils (RCC) in Ghana, NDPC, and Sector partners (MSWR, GES-SHEP, MoH). |  | WASH | Mixed | Capacity | Planning | https://twitter.com/IRC_Ghana/status/1660967716365258755
9 | Output | Ghana | Plan | Training event for at least 30 persons using the WASH Systems Academy (CONIWAS members) - Advocating for universal WASH services and Fundraising for WASH for NGOs and CSOs | Yes | IRC Ghana organised a WASH system academy training workshop with CONIWAS and its members on Advocating for universal WASH services and Fundraising for WASH for NGOs and CSOs in Tamale. |  | WASH | Mixed | Capacity | Regulation Accountability | https://www.linkedin.com/posts/coniwas-ghana_washadvocacy-fundraisingsuccess-washchampions-activity-7135562375482478592-Qcow?utm_source=share&utm_medium=member_desktop
10 | Output | Ghana | Plan | Knowledge product : State of water services in 14 districts in the Western Region, Ghana | Yes | This report presents the findings of water services in the western region of Ghana. It gives a comprehensive overview on water infrastructure, services and stakeholders in the Western Region and aims to support sector strengthening and learning, a key element of supporting CWSA’s change journey. |  | Water | Mixed | Models | Monitoring | https://www.ircwash.org/news/state-water-services-western-region-ghana
11 | Output | Ghana | Plan | Masterplans in 3 new districts (Asunafo North, Asunafo South, Tano North) in Ahafo Region | Yes | Masterplans have been prepared by the three additional districts and approved by the respective assemblies. Thses costed masterplans provide the framework for coordinating interventions, moblising resources, and attracting new partners for the implementation of the plans to achieve thw 2030 targets set. |  | WASH | Mixed | Strong Systems |  | https://www.ircwash.org/news/ghana-new-wash-master-plans-scale-innovations-universal-WASH-coverage
12 | Output | Ghana | Plan | Improve access to safe sanitation and hygiene services in 5 schools, 2 healthcare facilities and to 60 vulnerable families (Asutifi North) | Yes | IRC, in partnership with the Church of Latter-Day Saints Charities, successfully improved sanitation and hygiene in 5 schools, 2 healthcare facilities, and aided 60 vulnerable families in Asutifi North. This initiative benefited 240 vulnerable individuals, 1426 students, and 4336 healthcare patrons. Notably, there was a 68% reduction in open defecation across 25 communities, with a 10% increase in school sanitation access and an 11% improvement in hygiene infrastructure. The collaboration has significantly enhanced community well-being and sustainability. |  | Sanitation | Mixed | Strong Systems | Infrastructure | https://www.anamwash.com/blog/improving-sanitation-through-community-led-actions
13 | Output | Ghana | Plan | Peer learning amongst Asutifi North and the three new districts to promote the uptake of successful innovations. | Yes | IRC in collaboration with the Ahafo Regional Coordinating Council have setup a Regional Learning Alliance Platform serves as a forum for sharing best practices, experiences, and research findings specific to WASH and related areas in the Ahafo Region.At the maiden event, insights into the state of WASH services in the region was shared and discussed. Lessons learnt from the initial pilot in Asutifi North district were shared with the replication districts to inform uptake and serve as a catalyst for progress in acheving universal access to WASH services. |  | WASH | Mixed | Strong Systems | Learning and Adaptation | https://www.ircwash.org/events/ahafo-regional-level-learning-alliance-platform-rllap-meeting
15 | Output | Mali | Plan | Un dispositif de monitoring communal des services AEPA et des services sociaux de base est mis en place | Yes | L'élaboration d'un cadre de monitoring spécifique à chaque commune pour les services d'Approvisionnement en Eau Potable et Assainissement (AEPA) a permis de mieux évaluer et améliorer la qualité de ces services. Les ateliers de lancement et les diagnostics approfondis ont jeté les bases d'un plan d'action annuel budgétisé, visant une gestion plus efficace et transparente des services WASH |  | WASH | Rural | Models | Monitoring
16 | Output | Mali | Plan | Les populations vivant dans les 3 communes ont un accès durable aux services d'eau, d’hygiène et d’assainissement grâce à l'amélioration des services | Yes | Grâce à l'appui fourni aux communes pour la mise en œuvre de leurs plans d'action et à la mise en place d'équipes WASH FIT dans les établissements de santé, ainsi qu'au soutien aux Comités de Gestion des Établissements Scolaires (COGES) pour la gestion des infrastructures d'eau, d'hygiène et d'assainissement, les populations des trois communes bénéficient désormais d'un accès amélioré et durable à ces services vitaux |  | WASH in institutions | Rural | Capacity | Planning
17 | Output | Mali | Plan | Les communes bénéficiaires ont les capacités accrues pour une meilleure coordination multisectorielle pour une offre adéquate de services d’EHA | Yes | L'appui aux communes pour l'établissement de services techniques communaux AEPA, la création de cadres de concertation, et la formalisation de collaborations avec les services techniques de l'État a amélioré la coordination multisectorielle. Cela a permis une offre plus adéquate et cohérente de services WASH, renforçant ainsi la gouvernance locale dans ce secteur |  | WASH | Rural | Strong Systems | Regulation Accountability
18 | Output | Mali | Plan | Les capacités d’acteurs stratégiques nationaux sont renforcées en matière d'assistance technique aux collectivités pour la gouvernance des services d'eau potable et d'assainissement | Yes | L'atelier national de validation du cadre de monitoring communal a contribué à renforcer les compétences des acteurs stratégiques nationaux, leur permettant d'offrir une assistance technique plus efficace aux collectivités. Ce renforcement des capacités est essentiel pour la gestion durable des services d'eau potable et d'assainissement, soutenant les efforts de gouvernance à tous les niveaux |  | WASH | Mixed | Models | Learning and Adaptation
19 | Output | Mali | Plan | Appui à l'établissement d'une référence nationale pour le WASH en milieu de soins : appui dans la création d'un diagnostic national précis, facilitant la planification et l'amélioration ciblée des conditions sanitaires dans les établissements de santé | No |  |  | WASH in institutions | Mixed | Strong Systems | Planning
20 | Output | Mali | Plan | Production d'une vidéo documentaire pour la capitalisation | Yes | La réalisation d'une vidéo documentaire sur les interventions WASH dans les communes de Nossombougou, Ouolodo, et Tioribougou a permis de capturer et de partager visuellement les succès et les leçons apprises |  | WASH | Mixed | Strong Systems | Learning and Adaptation
21 | Output | Mali | Plan | Renforcement de la mobilisation de ressources : Augmentation significative de l'engagement de la diaspora envers le financement des projets WASH grâce à un appui ciblé, améliorant l'accès à l'eau et à l'assainissement | Yes | Cet appui a renforcé les capacités de la CN-CIEPA à mobiliser des ressources auprès de la diaspora pour le financement des projets WASH, contribuant ainsi à une meilleure gestion des ressources en eau et à l'assainissement au Mali |  | WASH | Mixed | Political & financial commitment | Finance
22 | Output | Mali | Plan | Amélioration de la gestion des services municipaux d'eau et d'assainissement : Les mairies ont bénéficié d'un soutien renforcé, résultant en une gestion plus efficace et durable des SMEA dans les communes concernées | Yes | Cet appui a amélioré les capacités opérationnelles et de gestion des SMEA, assurant une meilleure fourniture de services WASH à la population locale |  | WASH | Rural | Capacity | Institutions
23 | Output | Mali | New Output | Amélioration du suivi des projets WASH : Implémentation réussie d'outils de monitoring adaptés, permettant un suivi précis et une évaluation de l'impact des interventions sur le terrain | Yes | La mise en place d'outils de monitoring a permis un meilleur suivi et évaluation des projets WASH, garantissant l'efficacité et l'impact des interventions sur le terrain |  | WASH | Mixed | Models | Monitoring
24 | Output | Mali | Plan | Actualisation des données sur l'accès au WASH : Réalisation d'enquêtes JMP institutionnel fournissant des données à jour essentielles pour la planification et l'optimisation des ressources dans les communes ciblées | Yes | L'enquête a fourni des données actualisées sur l'accès à l'eau potable et à l'assainissement dans , crucial pour la planification future et l'allocation des ressources |  | WASH in institutions | Rural | Strong Systems | Monitoring
25 | Output | Mali | Plan | Renforcement de la coordination et de l'efficacité des stratégies WASH : La taskforce a bénéficié d'un appui consolidé, améliorant la mise en œuvre des interventions WASH à travers le pays | Yes | Cet appui a renforcé les capacités de la taskforce à coordonner et à mettre en œuvre des stratégies WASH efficaces, contribuant à l'amélioration des standards de santé publique au Mali |  | WASH in institutions | Mixed | Strong Systems | Learning and Adaptation
26 | Output | Mali | New Output | Amélioration de la gestion des déchets médicaux : Participation à la validation d'un manuel révisé sur les normes et procédures de gestion des déchets issus de soins de santé dans le contexte One Health | Yes | La validation de ce manuel a renforcé les capacités des établissements de santé dans la gestion sécurisée des déchets, réduisant ainsi les risques d'infections et de contaminations |  | WASH in institutions | Mixed | Strong Systems | Policy & Legislation
27 | Output | Mali | New Output | Renforcement de la TASK FORCE WASH/PCI : Participation à la validation d'un plan de renforcement des capacités de la TASK FORCE | Yes | Ce plan vise à améliorer les compétences et les connaissances des membres de la TASK FORCE en matière de WASH et de prévention et contrôle des infections (PCI), essentiel pour la qualité des soins |  | WASH in institutions | Mixed | Partnership | Planning
28 | Output | Mali | New Output | Accroissement des compétences en WASH FIT 2.0 : Formation des membres de la TASK Force, augmentant l'efficacité de l'évaluation, du suivi et de l'amélioration des pratiques WASH dans les établissements de santé | Yes | Cette formation a équipé les membres de la taskforce de connaissances et de compétences avancées pour l'évaluation, le suivi et l'amélioration des pratiques WASH dans les établissements de santé |  | WASH in institutions | Mixed | Strong Systems | Learning and Adaptation
29 | Output | Mali | New Output | Assurance qualité de la durabilité des services WASH : Partcipation en tant que assureur qualité des données collectées pour mesurer la durabilité des services WASH en collaboration avec la CPS et l'UNICEF | No |  |  | WASH | Mixed | Strong Systems | Monitoring
30 | Output | Mali | New Output | Introduction de l'approche systémique dans les projets WASH du consorsium SWSC : Consultance auprès de SWSC sur l'approche systémique adoptée qui a permis de mieux comprendre et adresser les défis au sein des projets, assurant des améliorations durables de l'accès à l'eau et à l'assainissement | No |  |  | WASH in institutions | Mixed | Strong Systems | Learning and Adaptation
31 | Output | Niger | Plan | The national roadmap and associated costed action plan for achieving SDG 6 in HCFs is developed and implemented | Yes | The activity is ongoing. The working group and multi-sector steering committee have been set up. The surveyors responsible for data collection have been trained (by the CDC), and sampling will be carried out shortly, followed by data collection, on the basis of which the roadmap and its costed action plan will be drawn up. The roadmap and its costed action plan will serve to inform decision-makers of what is needed to achieve the commitments related to SDG6 in HCFs and as an advocacy tool to mobilize more funding for WASH in HCFs. |  | WASH in institutions | Mixed | Strong Systems | Finance | https://ircwash.sharepoint.com/:f:/s/NigerBusinessUnit/EjWW3DIrLZ9In8sn9yOOtUwBUiBLdjt2c_RdgpOmmwnlPw?e=lpGc3g
32 | Output | Niger | Plan | National advocacy strategy for improved WASH in schools developed and implemented | No
33 | Output | Niger | Plan | Additional financial resources are acquired | Yes | During the year, the programme succeeded in mobilizing new funding of US$150,000. This fund will enable the programme to continue its system-strengthening activities at national and local levels. |  | WASH | Mixed |  | not applicable | https://ircwash.sharepoint.com/:f:/s/NigerBusinessUnit/EuFW1rus_e1BvBU8PdCesFsBQlJiV_dBOYxUfdm19BJU2g?e=atBoDc
34 | Output | Niger | Plan | The sector wide sustainability check study is completed | Yes | The activity is ongoing. The sector wide sustainability control study has been launched. Within this framework, IRC is providing technical assistance to the Ministry of Hydraulics, Sanitation and the Environment and UNICEF. A technical committee has been set up (IRC is part of the committee). The international consultancy firm responsible for carrying out the study has been recruited (IRC took part in drafting the ToR and in the recruitment process). A meeting between IRC, UNICEF, the Ministry and the consultancy firm is scheduled. Following this meeting, the study can begin. Following the study, a sector-wide sustainability compact will be drawn up. The programme could play a role in monitoring the implementation of the compact. |  | WASH | Mixed | Models | Monitoring | https://ircwash.sharepoint.com/:f:/s/NigerBusinessUnit/EkttE6Lqp7pCuivKtkImbs4B99O3SqI4ww2Y09isN-2qoQ?e=WbB9jV
35 | Output | Niger | Plan | Conduct advocacy for improved WASH services in health centers | Yes | At communal level, IRC carried out advocacy activities (workshop and implementation of WASH FIT action plans) for the improvement of WASH services in healthcare facilities for communal authorities, health center managers, NGOs and the community. |  | WASH in institutions | Rural | Political & financial commitment | Finance | https://ircwash.sharepoint.com/:f:/s/NigerBusinessUnit/EhyX0ZzekX1Ij9Cmi79iqA8B7DSA4uLZScwlkGmqoe-aDQ?e=6Bk4mr
36 | Output | Niger |  | Assess WASH system building blocks, SDG 6 intermediate outcomes and SWA partnership indicators | No
37 | Output | Niger |  | Support the operationalization of coordination tools through IRC involvement in the WASH sector at the national level | Yes | IRC funded the WASH FIT technical working group to contextualize the WASH FIT 2.0 tool to the Niger context. IRC also supported the WASH accounts technical group and steering committee for their first review meetings. For the program, this output is important as it provides an official national document for the WASH FIT 2.0 and the implementation plan for the WASH accounts process. |  | WASH | Mixed | Partnership | not applicable | https://ircwash.sharepoint.com/:f:/s/NigerBusinessUnit/Ek1U25S5vfFAiv_gSfLPY_EBc3VhTKFt32KcYCmPlX8nfg?e=FUYGam
38 | Output | Niger |  | Develop the District Strategic Plan for Water, Sanitation and Hygiene (masterplan) for the district focus | Yes | The activity is ongoing. IRC has launched the masterplanning process for the municipality of Kornaka. The motivation and mobilization workshop was held and the ad hoc committee responsible for drawing up the master plan was set up. Having a master plan in place in the partner commune is essential to achieving the program's objectives (enabling the commune to achieve SDG6). |  | WASH | Rural | Strong Systems | Planning | https://ircwash.sharepoint.com/:f:/s/NigerBusinessUnit/Eh6Hb6idBVFHuTARf5jvnDEBQv5Aewqzte8uyON8FnVYsw?e=s6JtGm
39 | Output | Niger |  | Provide institutional support to partner districts to carry out the responsibilities transferred to them by the State in the WASH sector | Yes | IRC has a communal technical assistant in the commune of Kornaka who assists the commune and the municipal water and sanitation officer in exercising the powers transferred by the State to communes in the WASH sector. This is important for the program, as it creates a favorable environment for the implementation of these powers. |  | WASH | Rural | Capacity | Institutions | https://ircwash.sharepoint.com/:f:/s/NigerBusinessUnit/EhP2qIiuylFEnkygOS-oMyEBemF7SwFWcpmcG8h3ZCAyzA?e=w6xoaw
40 | Output | Niger |  | Implementation of the WASH FIT process in the focus district | Yes | IRC is implementing the WASH FIT approach in 6 healthcare facilities to improve WASH services in these facilities. |  | WASH in institutions | Rural | Capacity | Institutions | https://ircwash.sharepoint.com/:f:/s/NigerBusinessUnit/Eu5Rq_H9KsxKoPN1UzoGjV0B2MSN-t6cVJ9dyKnpLMzl8A?e=eddWgR
41 | Output | Niger |  | Workshops to build the capacity of civil society to protect and defend citizens and users of public services using a human rights-based approach. | No
42 | Output | Niger |  | Build the capacity of the private sector to provide sustainable, accessible, affordable and reliable WASH services. | No
43 | Output | Uganda | Plan | Implement the Joint Uganda D30 Alliance Strategy with a focus on Resource mobilization, entry into Kyenjojo district, rollout the communication and media engagement roadmap and strengthen national and district WASH systems. | Yes | During the year, IRC together with WfP received grants from Osprey Foundation, Waterloo, UNOPS (Sanitation and Hygiene Fund), held an entry meeting into Kyejonjo as joint district of implementation under One For All alliance, supported various programme interventions (including capacity building) in Kabarole and Bunyangabu with focus on WASH system strengthening. |  | WASH | Rural | Partnership | Planning
44 | Output | Uganda | Plan | Finalize the establishment of the monitoring data portals for Kabarole and Bunyangabu and upgrade the Bunyangabu WASH Roadmap to the WASH Masterplan. | Yes | District WASH data portals for Kabarole and Bunyangabu were launched and Bunyangabu WASH Roadmap though not upgraded into full WASH masterplan was duly approved by the district council. |  | WASH | Rural | Strong Systems | Monitoring
45 | Output | Uganda | Plan | Co-convene the UWEWK 2023 and support meaningful participation of Uganda in the All Systems Connect 2023 symposium. | Yes | Organised a session (Innovative Financing mechanisms for WASH, Environment and Climate Change) during UWEWK2023 and selected IRC team together with officials from Ministries of Water (including AWMZ), Health, Finance and Kabarole DLG participated in ASC including delivering presentations and moderating sessions. |  | WASH | Mixed | Partnership | Learning and Adaptation
46 | Output | Uganda | Plan | Extend safe water supply to 2 communities in Bunyangabu and construct sanitation facilities in 2 schools and 1 HCF in Kabarole. | Yes | Commenced works for safe water supply in Bunyangabu and constructed sanitation facilities at 2 schools (Kiamara & Rwankenzi) and 3 HCFs (Kaswa HC III, Kabende HC III and Kasunganyanja HC III) |  | Water | Rural | Strong Systems | Infrastructure
47 | Output | Uganda |  | Conduct a study on WASH financing in HCFs. | Yes | This was revised to WASH in HCFs assessment and subsequently conducted (under partnership arrangement between IRC,CDC and IDI) in September 2023, regional/national validation and dissemination of assessment findings is scheduled for February 2024. |  | WASH | Urban | Partnership | Monitoring
48 | Output | Uganda |  | Produce and share documentation on state of WASH and implementation in Kabarole and Bunyangabu Districts. | No |  |  | WASH | Rural | Partnership | Learning and Adaptation
49 | Output | Uganda | Plan | Conduct high level WASH advocacy with the Parliament, WASH Agenda for Change Partners and other influencing groups to amplify community voices on the low public funding to WASH activities. | No |  |  | WASH | Mixed | Partnership | Learning and Adaptation
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Note on M11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Nana Yaa Korankyewa-Ayim check there seems to be a misalignment in column here